## Sheet1
Abb. | Name | Sr. no. | Task | CW_20 |  |  |  |  | CW_21 |  |  |  |  | CW_22 |  |  |  |  | CW_23 |  |  |  |  | CW_24 |  |  |  |  | CW_25 |  |  |  |  | CW_26
SS | Saee Saraf |  |  | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27
DK | Darshana Kumbhakarna | 1 | Group formation | CW_20 13: SS,DK,SK,DG
SK | Suyash Kumbharkar | 2 | Client order understanding | CW_20 14: SS,DK,SK,DG
DG | Dnyanesh Ghadi | 3 | Gitlab understanding and setup | CW_20 16: SS,DK,SK,DG
|  | 4 | Roles selection | CW_20 16: SS,DK,SK,DG
| Status | 5 | Roles understanding | CW_21 20: SS,DK,SK,DG
| in Process | 6 | Create and test JIRA tool | bar: CW_21 20 to CW_21 21
| Completed | 7 | UML design | CW_21 22: SS,DK,SK,DG
|  | 8 | Architecture of webpage | bar: CW_21 24 to CW_22 28
|  | 9 | Pre-requisites understanding | bar: CW_22 27 to CW_22 28
|  | 10 | Existing work research | CW_22 29: SS,DK,SK,DG
|  | 11 | UI design | bar: CW_22 31 to CW_23 7
|  | 12 | Data structure | bar: CW_23 3 to CW_23 7
|  | 13 | UI finalization (front end) | bar: CW_23 5 to CW_24 12
|  | 14 | Back end | bar: CW_23 7 to CW_24 12
|  | 15 | Integration of Front end and back end | CW_24 10: DK, SS
|  | 16 | Testing | bar: CW_24 13 to CW_25 18
|  | 17 | Project paper requirements | CW_25 18: SS,DK,SK,DG
|  | 18 | Docker understanding | CW_25 18: SK,DG
|  | 19 | Docker setup | bar: CW_25 21 to CW_26 27
|  | 20 | Submission | CW_25 21: SS,DK,SK,DG